## Sheet1
Week
Phase | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Description | Initial Plan | bar: Week 1
Project Research and Planning | Explore existing research | bar: Week 2 to Week 3
Find problems others have encountered | bar: Week 2
Research different makes and models of UAVs | bar: Week 2 to Week 3
Choose 4 models of UAVs to investigate | bar: Week 3
Brief investigation of the 4 models and plan how to proceed | bar: Week 3 to Week 4
Supervisor Meeting | bar: Week 4
Investigation | Find and extract evidence items | Week 8: More Time Needed; Week 9: More Time Needed
| Put findings into readable format | Week 8: More Time Needed; Week 9: More Time Needed
| Supervisor Meeting | Week 8: More Time Needed; Week 9: More Time Needed
Optional Programming | Decide if the program can be built | Week 8: Optional; Week 9: Optional
| Plan basic program that can assist in investigation | Week 8: Optional; Week 9: Optional
| Supervisor Meeting | Week 9: Optional
Exploration | Find other areas that can be researched | bar: Week 10
Look into these areas and see if it can be helpful for an investigation | bar: Week 10
Final Report | Final draft report
Evaluation / conclusion | bar: Week 11 to Week 12